# SEO Implementation — Quick Start Action Plan

Prepared for: Mohit, YantrAI Labs

Start Date: March 9, 2026

## What We Just Created For You

6 operational documents ready to execute:

YantrAI_Labs_SEO_Strategy.docx — Full strategy (reference)

01_Keyword_Research.xlsx — 10 target keywords, prioritized

02_Content_Calendar.xlsx — 6-month editorial calendar

03_SEO_Checklist.xlsx — 24 actionable tasks by phase

04_YCS_Page_Outline.docx — Ready-to-fill template

05_Solvr_Page_Outline.docx — Ready-to-fill template

06_Kiran_Page_Outline.docx — Ready-to-fill template

## WEEK 1 — FOUNDATION (Do These First)

### Priority 1: Website Audit (2-3 hours)

Visit your site and audit:

Meta tags: Are they optimized? (check 04_YCS_Page_Outline for examples)

Page structure: Is content organized logically?

Mobile: Does it work on phones?

Speed: Run Lighthouse (Chrome DevTools → Lighthouse tab)

Note findings in 03_SEO_Checklist.xlsx

### Priority 2: Setup Analytics (1 hour)

Go to Google Search Console (search.google.com):

Add your website property

Submit your sitemap (you may need to create one: /sitemap.xml)

Go to Google Analytics 4 setup → Create property for yantrailabs.com

### Priority 3: Start YCS Page (4-6 hours)

Open: 04_YCS_Page_Outline.docx

Fill in each [FILL] section with your content

Focus on:

H1 + Meta tags (most important for SEO)

2-3 case studies with numbers (ROI, efficiency gains)

Key benefits (250-300 words)

Target word count: 800-1000 words

## WEEK 2-3 — CONTENT & OPTIMIZATION

### If YCS Page is Done:

Publish it (add to site structure: yantrailabs.com/ycs)

Add schema markup (copy from 04_YCS_Page_Outline checklist)

Internal link from homepage to /ycs

### Start Content Calendar:

Open: 02_Content_Calendar.xlsx

Pick 2 blog topics from March (Week 1 & Week 3)

Assign deadlines to yourself

Write first blog post: "How to Implement AI in Your Enterprise"

Target keyword: "machine learning implementation"

Include: Overview (200 words) → Steps (400 words) → Case example (200 words)

### Submit to Directories:

GoodFirms.com — Submit YCS profile (free listing)

Clutch.co — Submit YCS + Solvr profiles (free listing)

Google Business Profile — Verify yantrailabs.com

## MONTH 2+ — SCALE & AUTHORITY BUILD

### Content:

Publish 1 blog post every 2-3 weeks (use 02_Content_Calendar)

Each post should link to relevant product page (YCS/Solvr/Kiran)

Aim for 800+ words, naturally include secondary keywords

### Backlinks:

Guest posts: Dev.to, Hashnode, Medium (3-5 per quarter)

Each guest post should link back to relevant page on yantrailabs.com

Broken link outreach (find dead resources, offer your content as replacement)

### Monitoring:

Weekly: Check Google Search Console for new rankings

Monthly: Check organic traffic in Google Analytics

Monthly: Update 01_Keyword_Research.xlsx with new rankings

## SUCCESS METRICS (3-Month Goals)

| Metric | Target |
| --- | --- |
| Organic traffic | 300-500 visits/month |
| Keywords in top 10 | 5-10 target keywords |
| Backlinks | 10-15 high-quality links |
| Lighthouse SEO score | 90+ |
| Core Web Vitals | All green (LCP < 2.5s) |

## ⚠️ Common Mistakes to Avoid

Keyword stuffing: Don't repeat keywords more than 2-3% of page

Thin content: Every page must have 500+ words (blog posts 800+)

Broken links: Check all internal links work before publishing

No internal linking: Link related pages to each other

Ignoring mobile: Test every page on phone

Forgetting schema: Every product page needs schema markup

## Tools You'll Need

Google Search Console — FREE, required

Google Analytics 4 — FREE, required

Ahrefs free tier OR SEMrush free tier — For keyword tracking

Lighthouse (in Chrome) — FREE, for performance audits

Screaming Frog — FREE, to crawl your site

## Next Step — Right Now

1. Open 03_SEO_Checklist.xlsx
2. Update status as you complete each task
3. Start with the YCS page (highest ROI)
4. Track everything there

You're building compounding SEO authority. Do the work consistently, and in 3 months you'll have 300-500 organic visitors/month. In 6 months, you'll own your niche keywords.