## Tasks
Phase | Task | Subtask | Owner | Timeline | Status | Priority | Notes
FOUNDATION | Website Audit | Crawl site with Screaming Frog | You | Week 1 | To Do | P1 | Identify technical issues
FOUNDATION | Website Audit | Check meta tags on all pages | You | Week 1 | To Do | P1 | Document gaps
FOUNDATION | Website Audit | Test mobile responsiveness | You | Week 1 | To Do | P1 | Check Core Web Vitals
FOUNDATION | Setup Analytics | Configure Google Search Console | You | Week 1 | To Do | P1 | Import sitemap
FOUNDATION | Setup Analytics | Setup Google Analytics 4 | You | Week 1 | To Do | P1 | Track organic traffic
FOUNDATION | Setup Analytics | Setup Ahrefs/SEMrush free trial | You | Week 1 | To Do | P1 | Keyword tracking
FOUNDATION | Create Product Pages | YCS Page: Write content (800-1000 words) | Mohit | Week 1-2 | To Do | P1 | Target: AI consulting services India
FOUNDATION | Create Product Pages | YCS Page: Add meta tags & schema | You | Week 2 | To Do | P1 | Use template provided
FOUNDATION | Create Product Pages | Solvr Page: Write content | Mohit | Week 2-3 | To Do | P2
FOUNDATION | Create Product Pages | Kiran Page: Write content | Mohit | Week 3-4 | To Do | P2
FOUNDATION | Technical SEO | Implement Organization schema (homepage) | You | Week 2 | To Do | P1
FOUNDATION | Technical SEO | Implement Product schema (product pages) | You | Week 2 | To Do | P1
FOUNDATION | Technical SEO | Create XML sitemap | You | Week 2 | To Do | P1 | Submit to GSC
FOUNDATION | Technical SEO | Optimize page speed | You | Week 2-3 | To Do | P2 | Target: < 2.5s mobile
CONTENT | Blog Post 1 | Research & outline (Machine Learning Implementation) | Mohit | Week 2 | To Do | P1
CONTENT | Blog Post 1 | Write & SEO optimize | Mohit | Week 2-3 | To Do | P1
CONTENT | Blog Post 1 | Publish & promote | You | Week 3 | To Do | P1 | Link to YCS page
CONTENT | Blog Post 2 | Research & outline (Rapid App Development) | Mohit | Week 3 | To Do | P1
AUTHORITY | Backlink Building | Submit to GoodFirms | You | Week 2-3 | To Do | P1 | YCS profile
AUTHORITY | Backlink Building | Submit to Clutch | You | Week 2-3 | To Do | P1 | YCS + Solvr
AUTHORITY | Backlink Building | Guest post outreach (Dev.to, Hashnode) | Mohit | Week 3-4 | To Do | P1 | Target: 5 posts
AUTHORITY | Brand Mentions | Add company to Startup India | You | Week 3 | To Do | P2
AUTHORITY | PR Outreach | Press release: Major milestone | Mohit | Week 4 | To Do | P2 | If milestone exists